## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | team-project-2191-swen-261-01-c-parkerswithoutparker
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
| Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass |  | Pass |  | Pass
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass |  | Pass |  | Pass
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | Duplicate names have not been addressed yet. PJ (10/9) Fixed. EC 10/14 | Pass |  | Pass
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass |  | Pass |  | Pass
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | Duplicate names have not been addressed yet. PJ (10/9) Fixed. EC 10/14 | Pass |  | Pass
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass |  | Pass |  | Pass
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass |  | Pass |  | Pass
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass |  | Pass |  | Pass
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass |  | Pass |  | Pass
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Fail | Not implemented. PJ (10/9) 500 Internal Server Error. EC (10/15) | Fail | 500 Server Error PJ (11/2) | Pass
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | Not implemented. PJ (10/9) Fixed. EC (10/15) | Pass |  | Pass
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass |  | Pass |  | Pass
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | Pieces on board not implemented. PJ (10/9) Fixed. EC (10/15) | Pass |  | Pass
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | Pieces on board not implemented. PJ (10/9) Fixed. EC (10/15) | Pass |  | Pass
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | Pieces on board not implemented. PJ (10/9) Fixed. EC (10/15) | Pass |  | Pass
As a player I want to jump over opponent pieces so that I can take their pieces off the board. | Given any piece on the board when another piece jumps over it then that piece is taken off the board. |  |  | Pass |  | Pass
| Given a normal piece when there is an empty adjacent space then I can move once to that space in any direction EXCEPT backwards. |  |  | Pass |  | Pass
| Given checkers'rules when I line up a checker to capture the opponent then I expect to be able to jump over their checker |  |  | Pass |  | Pass
| Given a normal piece when there is an adjacent opponents piece than I should be able to jumo over that checker in any direction except backwards. |  |  | Pass |  | Pass
| Given a normal piece on the board when the piece reaches the farthest row then that piece becomes a King piece |  |  | Pass |  | Pass
| Given a King piece when there is an empty adjacent space then I can only move once to that space in any direction. |  |  | Pass |  | Pass
| Given a King piece when there is an adjacent opponents piece than I should be able to jump over that checker in any direction. |  |  | Pass |  | Pass
| Given any piece on the board when there is an adjacent allied piece than I cannot jump over that piece ever. |  |  | Pass |  | Pass
| Given a checkers game when one color is completely removed from the board via jumping then the player controlling that color loses the match and the game ends. |  |  | Fail | Taking all pieces does nothing. One must resign to end a game. PJ(11/3) | Pass
| Given a checkers game when I jump over the last opponents piece than i should win the match and the game ends. |  |  | Fail | Taking all pieces does nothing. One must resign to end a game. PJ(11/3) | Pass
As a Player I want to resign a game so that I can stop playing checkers. | Given a game of checkers when I press resign then I expect to lose immediately. |  |  | Pass |  | Pass
| Given a game of checkers when my opponent resigns then I shoulkd see a message saying so and an option to exit. |  |  | Pass |  | Pass
As a Player I want to backup/undo a move so that I can make another move on the same turn. | Given I move a piece on the board when I click on the Backup button then my piece should move back to the original position. |  |  | Pass |  | Pass
As a Player I want to click the submit turn button so that i can finalize my move and end my turn. | Given my move when I click on the submit turn button then the opponents turn is up and my move is finalized. |  |  | Pass |  | Pass
| Given my opponents move when they click on the submit button then it becomes my turn and they cannot move again. |  |  | Pass |  | Pass
As a Player I want to be able to jump over multiple pieces so that I can take multiple opponents' checkers. | Given checker's rules when I jump over one opponent piece and I can jump again then I should jump over that piece. |  |  | Pass |  | Pass
| Given any piece on the board when I jump over one opponent piece then I cannot jump over that piece again |  |  | Pass |  | Pass
| Given a King piece on the board when I jump over one opponent piece then I can jump over any piece again in any direction. |  |  | Pass |  | Pass
| Given any piece on the board when I jump over one opponent piece and there is another available jump then I cannot submit that 1 jump as my turn. |  |  | Fail | In some cases, you can submit the 1 jump turn. In others you can't PJ (11/3) | Pass
As a Player I want to see my game statistics so that I can determine how good I am at the game. | Given I have signed in when I am at the home page then I should be able to see statistics pertaining to my username, such as number of games played, number of games lost/won, number of pieces taken/lost and the W/L ratio. |  |  |  |  | Pass
| Given I have signed in when I am at the home page then I should be able to see a leaderboard of stats for all other usernames that have ever been logged in. |  |  |  |  | Pass
| Given the leaderboard of stats when I click on one of the filter buttons then the leaderboard's ordering should change based on that filter. |  |  |  |  | Pass
| Given I have finished a game of checkers when I go back to the home screen then my stats should update given how the game went, how many pieces I took/lost and whether I won or not. |  |  |  |  | Pass
As a Player I want to have a Help button in-game so that I can receive more assistance during my turn if I need it | Given I am playing a game of checkers when I click the HELP button then all available moves that I can make should be highlighted on the board |  |  |  |  | Pass
| Given I am playing a game of checkers and click the HELP button when there is a jump to be made then the help function will only highlight required jumps |  |  |  |  | Pass
| Given I am playing a game of checkers and click the HELP button when I click REMOVE HELP then all highlighted spaces should disappear and the board should go back to normal |  |  |  |  | Pass
| Gvien I am playing a game of checkers and click the HELP button when I try to make a move without clicking REMOVE HELP then I should not be able to do so until I click REMOVE HELP |  |  |  |  | Pass